## Sheet2
Dissertation Gantt Chart |  | October |  |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March
Date Start |  | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27
Dissertation Proposal | Aims and Objectives | 2024-11-04: Reading Week; 2024-12-16: Winter Break
Research Methods | bar: 2024-09-30 to 2024-10-07
Data Exploration | bar: 2024-10-07
Gantt Chart | bar: 2024-09-30 to 2024-10-14
Proposal | bar: 2024-10-14 to 2024-10-21
Research | Supervisor Meeting | bar: 2024-10-14
Reading, understanding mathematical basis | bar: 2024-10-07 to 2024-10-28
UMEP and SUEWS practice in qGIS | bar: 2024-10-14 to 2024-11-04
Learn Python/SuPy | bar: 2024-10-21 to 2024-11-11
Chat with Dr Ting Sun | bar: 2024-10-14
Data Download and Preprocessing | bar: 2024-11-04 to 2024-11-18
Data Analysis | bar: 2024-11-18 to 2024-12-02
Producing results/maps | bar: 2024-12-02 to 2024-12-09
Annotated Bibliography | bar: 2024-10-07 to 2024-11-11
Finalize Literature Review | bar: 2024-11-11 to 2024-12-16
Preliminary | Formatting and Structure | bar: 2024-11-18 to 2024-11-25
Acknowledgments | bar: 2024-12-02
Methodology | bar: 2024-11-25 to 2024-12-09
Preface | bar: 2024-12-09 to 2024-12-23
Writing | Abstract
Results | bar: 2024-12-02 to 2024-12-23
Discussion | bar: 2024-12-09 to 2025-01-13
Conclusion | bar: 2024-12-16 to 2025-01-20
Evaluation/ Auto critique | bar: 2024-12-23 to 2025-01-06
Word Limit check | bar: 2024-12-30 to 2025-02-03
Feedback | Dr Ting Sun | bar: 2024-11-11 to 2024-12-09; 2025-01-20 to 2025-01-27
| Supervisor Dr Chris Brierley | 2025-02-10: deadline
Finalization | Proof-reading | bar: 2025-01-13 to 2025-03-03
Editing | bar: 2025-02-24 to 2025-03-10
Print out | bar: 2025-03-17
Submission | bar: 2025-03-24